## SME GROWTH HUB
Status | Task Name | Priority | Assigned To | Notes | Start Date | Finish Date | Duration | Predecessors | Percentage Complete | Baseline Start | Baseline Finish | Variance
Status Key
Red | Not Started
Yellow | On Hold
Green | In Progress
Blue | Complete
Green | SME GOWTH HUB |  |  |  | 2024-01-21 | 2024-09-30 | 182d |  |  | 2024-01-21 | 2024-09-30 | 0
Blue | Planning and Preparation Phase | High | Project Manager |  | 2024-01-21 | 2024-02-02 | 11d |  | 1 | 2024-01-21 | 2024-02-02 | 0
Blue | Define Project Scope and Objectives | High | Project Manager |  | 2024-01-21 | 2024-01-29 | 7d |  | 1 | 2024-01-21 | 2024-01-29 | 0
Blue | Identify key features and services of SME Growth hub. | High | Project Manager |  | 2024-01-21 | 2024-01-23 | 3d |  | 100 | 2024-01-21 | 2024-01-23 | 0
Blue | Set project goals and objectives | High | Project Manager |  | 2024-01-24 | 2024-01-29 | 4d | 10 | 100 | 2024-01-24 | 2024-01-29 | 0
Blue | Assemble Project Team | High | Project Manager |  | 2024-01-30 | 2024-01-31 | 2d |  | 1 | 2024-01-30 | 2024-01-31 | 0
Blue | Appoint key team members. | High | Project Manager |  | 2024-01-30 | 2024-01-30 | 1d | 11 | 100 | 2024-01-30 | 2024-01-30 | 0
Blue | Clarify roles and responsibilities. | High | Project Manager |  | 2024-01-31 | 2024-01-31 | 1d | 13 | 100 | 2024-01-31 | 2024-01-31 | 0
Blue | Stakeholder Analysis and Engagement | High | Project Manager |  | 2024-02-01 | 2024-02-02 | 2d |  | 1 | 2024-02-01 | 2024-02-02 | 0
Blue | Identify and engage with key stakeholders | High | Project Manager |  | 2024-02-01 | 2024-02-01 | 1d | 14 | 100 | 2024-02-01 | 2024-02-01 | 0
Blue | Determine their roles and level of involvement | High | Project Manager |  | 2024-02-02 | 2024-02-02 | 1d | 16 | 100 | 2024-02-02 | 2024-02-02 | 0
Blue | Develop Project Plan and Schedule | High | Project Manager |  | 2024-02-02 | 2024-02-02 | 1d |  | 1 | 2024-02-02 | 2024-02-02 | 0
Blue | Outline tasks, milestones, and timelines. | High | Project Manager |  | 2024-02-02 | 2024-02-02 | 1d |  | 100 | 2024-02-02 | 2024-02-02 | 0
Blue | Establish dependencies and resource allocation | High | Project Manager |  | 2024-02-02 | 2024-02-02 | 1d |  | 100 | 2024-02-02 | 2024-02-02 | 0
Red | Platform Development Phase | High | Technology Lead |  | 2024-02-05 | 2024-04-22 | 56d |  |  | 2024-02-05 | 2024-04-22 | 0
Red | Platform Design and Features | High | Technology Lead |  | 2024-02-05 | 2024-03-13 | 28d |  |  | 2024-02-05 | 2024-03-13 | 0
Red | Work with designers and developers to finalize platform design and features. | High | Technology Lead |  | 2024-02-05 | 2024-03-05 | 22d | 20 |  | 2024-02-05 | 2024-03-05 | 0
Red | Determine necessary integrations and functionalities. | High | Technology Lead |  | 2024-03-06 | 2024-03-13 | 6d | 23 |  | 2024-03-06 | 2024-03-13 | 0
Red | Develop Minimum Viable Product (MVP) | High | Technology Lead |  | 2024-03-14 | 2024-04-05 | 17d |  |  | 2024-03-14 | 2024-04-05 | 0
Red | Start building the core features of the platform. | High | Technology Lead |  | 2024-03-14 | 2024-03-28 | 11d | 24 |  | 2024-03-14 | 2024-03-28 | 0
Red | Conduct internal testing and iterations. | High | Technology Lead |  | 2024-03-29 | 2024-04-05 | 6d | 26 |  | 2024-03-29 | 2024-04-05 | 0
Red | User Testing and Feedback | High | Technology Lead |  | 2024-04-08 | 2024-04-22 | 11d |  |  | 2024-04-08 | 2024-04-22 | 0
Red | Release MVP to a select group for testing and feedback. | High | Technology Lead |  | 2024-04-08 | 2024-04-15 | 6d | 27 |  | 2024-04-08 | 2024-04-15 | 0
Red | Iterate based on user input. | High | Technology Lead |  | 2024-04-16 | 2024-04-22 | 5d | 29 |  | 2024-04-16 | 2024-04-22 | 0
Red | Content Creation and Partnerships Phase | High | Business Development Manager |  | 2024-04-23 | 2024-07-08 | 55d |  |  | 2024-04-23 | 2024-07-08 | 0
Red | Content Development | High | Business Development Manager |  | 2024-04-23 | 2024-05-24 | 24d |  |  | 2024-04-23 | 2024-05-24 | 0
Red | Create SME development content such as business skills courses, funding programs posts and mentorship programs. | High | Business Development Manager |  | 2024-04-23 | 2024-05-14 | 16d | 30 |  | 2024-04-23 | 2024-05-14 | 0
Red | Ensure content aligns with platform goals and user needs. | High | Business Development Manager |  | 2024-05-15 | 2024-05-24 | 8d | 33 |  | 2024-05-15 | 2024-05-24 | 0
Red | Partnership Development | High | Business Development Manager |  | 2024-05-27 | 2024-07-08 | 31d |  |  | 2024-05-27 | 2024-07-08 | 0
Red | Identify and cultivate partnerships with industry experts, mentors, investors, and support organizations. | High | Business Development Manager |  | 2024-05-27 | 2024-06-25 | 22d | 34 |  | 2024-05-27 | 2024-06-25 | 0
Red | Establish collaboration agreements and partnerships. | High | Business Development Manager |  | 2024-06-26 | 2024-07-08 | 9d | 36 |  | 2024-06-26 | 2024-07-08 | 0
Red | Marketing and Launch Phase | High | Marketing Manager |  | 2024-07-09 | 2024-08-07 | 22d |  |  | 2024-07-09 | 2024-08-07 | 0
Red | Develop Marketing Strategy and Materials | High | Marketing Manager |  | 2024-07-09 | 2024-07-24 | 12d |  |  | 2024-07-09 | 2024-07-24 | 0
Red | Create a comprehensive marketing plan, including digital campaigns, social media, and content marketing. | High | Marketing Manager |  | 2024-07-09 | 2024-07-16 | 6d | 37 |  | 2024-07-09 | 2024-07-16 | 0
Red | Prepare marketing materials and promotional content. | High | Marketing Manager |  | 2024-07-17 | 2024-07-24 | 6d | 40 |  | 2024-07-17 | 2024-07-24 | 0
Red | Pre-Launch Marketing Campaigns | High | Marketing Manager |  | 2024-07-25 | 2024-08-07 | 10d |  |  | 2024-07-25 | 2024-08-07 | 0
Red | Start pre-launch marketing campaigns to build anticipation. | High | Marketing Manager |  | 2024-07-25 | 2024-07-31 | 5d | 41 |  | 2024-07-25 | 2024-07-31 | 0
Red | Generate buzz and attract initial users. | High | Marketing Manager |  | 2024-08-01 | 2024-08-07 | 5d | 43 |  | 2024-08-01 | 2024-08-07 | 0
Red | Launch and Post-Launch Optimization Phase | High | Project Team |  | 2024-08-08 | 2024-09-30 | 38d |  |  | 2024-08-08 | 2024-09-30 | 0
Red | Platform Launch | High | Project Team |  | 2024-08-08 | 2024-08-15 | 6d |  |  | 2024-08-08 | 2024-08-15 | 0
Red | Officially launch SME Growth Hub. | High | Project Team |  | 2024-08-08 | 2024-08-08 | 1d | 44 |  | 2024-08-08 | 2024-08-08 | 0
Red | Monitor platform performance and user engagement. | High | Project Manager and Data Analyst |  | 2024-08-09 | 2024-08-15 | 5d | 47 |  | 2024-08-09 | 2024-08-15 | 0
Red | Post-Launch Optimization | High | Project Manager |  | 2024-08-16 | 2024-09-30 | 32d |  |  | 2024-08-16 | 2024-09-30 | 0
Red | Analyze user feedback and make necessary adjustments to improve user experience. | High | Data Analyst |  | 2024-08-16 | 2024-08-30 | 11d | 48 |  | 2024-08-16 | 2024-08-30 | 0
Red | Implement additional features and enhancements based on user needs and market trends. | High | Technology Lead and Project Manager |  | 2024-09-02 | 2024-09-30 | 21d | 50 |  | 2024-09-02 | 2024-09-30 | 0